## Risk Tracking Template
Risk Tracking Template
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Probability
1 | Illness/Absence | Medium | Notify beforehand/ Adjust tasks accordingly | Low
2 | Time estimations greatly inaccurate | Low | Utilise stand-ups and proceed with updates | Low
3 | Resources unavailable when needed | High | Plan back-ups for crucial resources | Medium
4 | Subcontractor out of business | Medium | Offer in-house contracting until replaced | Medium
5 | Necessary technology doesn't exist | High | Alter requirements to use existing technology | Low
6 | 3rd party components aren't compatible | Medium | Complete checks before acquiring components | Medium
7 | Communication issues | High | Messaging server with all team members | High
8 | Loss of data | High | Have back-ups (cloud or physical) | High
9 | Service required is unavailable | Low | Find alternate services | Low
10 | Unfixable bug | Medium | Revert to backup | Medium
11
12
13
14
15
16
17
18
19

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.